## Activities
Activity Name | Type | Week | Responsible | Estimated Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 3
Feature Research | Requirements | 3 | Everyone | 6 | 6 | Done | Reseaching what people want | 0 | 0
Project Name | Design | 3 | Everyone | 0.5 | 0.25 | Done | Name of the App | 0.25 | 100
Software Requirements | Requirements | 3 | Tim | 1 | 1 | Done | Decide what software is needed | 0 | 0
GitHub Setup | Preparation | 3 | Everyone | 2 | 2 | Done | Create accounts and get access | 0 | 0
Java Learning | Preparation | 3 | Everyone | 10 | 10 | Done | Quick run through of Java for development | 0 | 0
Done
Done
Done
Done
Done
Done
Week 4
Plan/Create Features List | Preparation | 4 | Everyone | 1.5 | 1.5 | Done | Get a list of features for the app | 0 | 0
Research Social Media Integration | Preparation | 4 | Brandon | 2 |  | Ongoing | Research how to begin social media integration
Main Menu/General UI Design | Design | 4 | Everyone | 0.75 | 0.75 | Done | Design UI for main screen | 0 | 0
Create Use Cases for Features | Documentation | 4 | Everyone | 8 |  | Ongoing | Create use cases for features for Assignment 1
Design UI for Workout Plan Manager | Documentation | 4 | Alex | 2 |  | Ongoing | Design UI for workout plan manager
Design UI for Diet Management | Documentation | 4 | Trang | 2 |  | Ongoing | Design UI for diet management
Design UI for Progression Tracker | Documentation | 4 | Tim | 2 |  | Ongoing | Design UI for progression tracker
Design UI for Friends List | Documentation | 4 | Xinchi | 2 |  | Ongoing | Design UI for friends list
Design UI for GPS Running Tracker | Documentation | 4 | Chase | 2 |  | Ongoing | Design UI for gps running tracker
Design UI for Social Media Integration | Documentation | 4 | Brandon | 2 |  | Ongoing | Design UI for social media sharing
Week 5
Create Use Cases for Features | Documentation | 5 | Everyone | 8 | 8 | Done | Create use cases for features for Assignment 1 | 0 | 0
Design UI for Workout Plan Manager | Documentation | 5 | Alex | 2 |  | Ongoing | Design UI for workout plan manager
Design UI for Diet Management | Documentation | 5 | Trang | 2 |  | Ongoing | Design UI for diet management
Design UI for Progression Tracker | Documentation | 5 | Tim | 2 |  | Ongoing | Design UI for progression tracker
Design UI for Friends List | Documentation | 5 | Xinchi | 2 |  | Ongoing | Design UI for friends list
Design UI for GPS Running Tracker | Documentation | 5 | Chase | 2 |  | Ongoing | Design UI for gps running tracker
Design UI for Social Media Integration | Documentation | 5 | Brandon | 2 |  | Ongoing | Design UI for social media sharing
Download Andriod Studio Software | Development | 5 | Everyone | 2.5 |  | Ongoing | Get software installed to begin development
Review Information on Andriod Studio Tutorial Website | Preparation | 5 | Everyone | 8 |  | Ongoing | Get familiar with website to help begin development
Week 6
Design UI for Workout Plan Manager | Documentation | 6 | Alex | 2 | 0.3 | Done | Design UI for workout plan manager | 1.7 | 566.6667
Design UI for Diet Management | Documentation | 6 | Trang | 2 | 0.3 | Done | Design UI for diet management | 1.7 | 566.6667
Design UI for Progression Tracker | Documentation | 6 | Tim | 2 | 0.3 | Done | Design UI for progression tracker | 1.7 | 566.6667
Design UI for Friends List | Documentation | 6 | Xinchi | 2 | 0.3 | Done | Design UI for friends list | 1.7 | 566.6667
Design UI for GPS Running Tracker | Documentation | 6 | Chase | 2 | 0.3 | Done | Design UI for gps running tracker | 1.7 | 566.6667
Design UI for Social Media Integration | Documentation | 6 | Brandon | 2 | 0.3 | Done | Design UI for social media sharing | 1.7 | 566.6667
Download Andriod Studio Software | Development | 6 | Everyone | 2.5 | 3 | Done | Get software installed to begin development | -0.5 | 16.6667
Review Information on Andriod Studio Tutorial Website | Preparation | 6 | Everyone | 25 |  | Ongoing | Get familiar with website to help begin development
Week 7
Design UML Diagram for Project | Documentation | 7 | Brandon | 2 | 3 | Done | Design complete | -1 | 33.3333
Design UML Diagram for Project | Documentation | 7 | Tim | 2 | 3 | Done | Design complete | -1 | 33.3333
Design UML Diagram for Project | Documentation | 7 | Chase | 2 | 3 | Done | Design complete | -1 | 33.3333
Design UML Diagram for Project | Documentation | 7 | Trang | 2 | 3 | Done | Design complete | -1 | 33.3333
Design UML Diagram for Project | Documentation | 7 | Alex | 2 | 3 | Done | Design complete | -1 | 33.3333
Create UML Diagram for Database | Documentation | 7 | Chase | 1 | 1 | Done | Design complete | 0 | 0
User login functionality added to app | Development | 7 | Brandon | 3 |  | Ongoing | Implementation in progress
Design Logo and Choose team color | Design | 7 | Alex | 1 |  | Ongoing | Design in progress
Review Information on Andriod Studio Tutorial Website | Preparation | 7 | Everyone | 25 | 25 | Done | Everyone has looked at the tutorials
Done
Week 8
User login functionality added to app | Interfaces | 8 | Brandon | 3 |  | Ongoing | Need to set up to connect with Database
Design Logo and Choose team color | Design | 8 | Alex | 1 |  | Ongoing | Design in progress
Database setup | Development | 8 | Chase | 1 | 3 | Done | Database is now able to be connected to remotely | -2 | 66.6667
User profile Interface/Activity | Interfaces | 8 | Brandon | 1 |  | Ongoing | Relaying design to the actual app
Database setup | Development | 8 | Xingchi | 1 | 3 | Done | Database is now able to be connected to remotely
Database setup | Development | 8 | Trang | 1 | 3 | Done | Database is now able to be connected to remotely | -2 | 66.6667
Database setup | Development | 8 | Tim | 1 | 3 | Done | Database is now able to be connected to remotely | -2 | 66.6667
Create tables in Database | Development | 8 | Trang | 1 |  | Ongoing | Setting up tables to hold app data
Create tables in Database | Development | 8 | Tim | 1 |  | Ongoing | Setting up tables to hold app data
Week 9
Login funcitonality added to the app | Development | 9 | Brandon | 1 | 2 | Done | Screens are complete. But still need to check for user credentials and interact with database | -1 | 50
UI Complete for Statistics functionality | Development | 9 | Brandon | 1 | 2 | Done | Screens are implimented. But still need to pull data that is entered by user and have interaction with database | -1 | 50
UI Complete for Home screen | Development | 9 | Brandon | 1 | 1 | Done | Layout is implemented, need to refine to interact with database. Task will be created to get another member to implement database interaction. | 0 | 0
UI Complete for User profile screen | Development | 9 | Brandon | 1 | 1 | Done | Layout is implemented, need to refine to interact with database. Task will be created to get another member to implement database interaction. | 0 | 0
UI Complete for Diet screens | Development | 9 | Brandon | 1 | 2 | Done | Layout is implemented, need to refine to interact with database. Task will be created to get another member to implement database interaction. | -1 | 50
UI Complete for Workouts screens | Development | 9 | Brandon | 1 | 1 | Done | Layout is implemented, need to refine to interact with database. Task will be created to get another member to implement database interaction. | 0 | 0
UI Complete for Exercises screens | Development | 9 | Brandon | 1 | 2 | Done | Layout is implemented, need to refine to interact with database. Task will be created to get another member to implement database interaction. | -1 | 50
UI Complete for Friends List screens | Development | 9 | Brandon | 1 | 0.5 | Done | Layout is implemented, need to refine to interact with database. Task will be created to get another member to implement database interaction. | 0.5 | 100
Fixed bug for Logout not sending user to the Login screen | Development | 9 | Brandon | 1 | 2 | Done | Logout menu option now takes the user to login screen. | -1 | 50
Database Table Creation | Development | 9 | Tim | 2 | 2 | Done | Tables have been created to hold data. | 0 | 0
Database Table Creation | Development | 9 | Trang | 2 | 2 | Done | Tables have been created to hold data. | 0 | 0
Database Table Creation | Development | 9 | Chase | 2 | 2 | Done | Tables have been created to hold data. | 0 | 0
Design Logo and Choose team color | Design | 9 | Alex |  |  | Ongoing
Done
Week 10
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Week 11
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
Week 12
Planned
Done
Done
Done
Done
and so on
Note on C1: swami: This is useful for generating subtotals and reports
Note on D1: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on H1: swami: Insert your own comments
Note on I1: SE: This field is updated automatically

## SummaryData
Note: All data on this sheet updated automatically
Item |  | Week |  | Total Estimation Error % | Count | Average Estimation Error %
Criteria
Week | Week | Week | Week | Week | Week | Week | Week | Week | Week
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
EstimationError
Week1 |  | 1 |  | 0 | 0 | 0
Week2 |  | 2 |  | 0 | 0 | 0
Week3 |  | 3 |  | 100 | 5 | 20
Week4 |  | 4 |  | 0 | 2 | 0
Week5 |  | 5 |  | 0 | 1 | 0
Week6 |  | 6 |  | 3416.6667 | 7 | 488.0952
Week7 |  | 7 |  | 166.6667 | 6 | 27.7778
Week8 |  | 8 |  | 200 | 3 | 66.6667
Week9 |  | 9 |  | 350 | 12 | 29.1667
Week10 |  | 10 |  | 0 | 0 | 0
Activity |  |  |  |  | Actual Effort
Requirements |  |  |  |  | 7
Design |  |  |  |  | 1
Development |  |  |  |  | 34.5
Testing |  |  |  |  | 0
Interfaces |  |  |  |  | 0
Documentation |  |  |  |  | 25.8
Coordination |  |  |  |  | 0
Preparation |  |  |  |  | 38.5
Delivery |  |  |  |  | 0
Criteria
Type | Type | Type | Type | Type | Type | Type | Type | Type
Requirements | Design | Development | Testing | Interfaces | Documentation | Coordination | Preparation | Delivery
EstimationError |  | Total | Count | Average
Requirements |  | 0 | 2 | 0
Design |  | 100 | 2 | 50
Development |  | 566.6667 | 16 | 35.4167
Testing |  | 0 | 0 | 0
Interfaces |  | 0 | 0 | 0
Documentation |  | 3566.6667 | 13 | 274.359
Coordination |  | 0 | 0 | 0
Preparation |  | 0 | 3 | 0
Delivery |  | 0 | 0 | 0
Week-wise-Effort
Week1 |  | 1 |  |  | 0
Week2 |  | 2 |  |  | 0
Week3 |  | 3 |  |  | 19.25
Week4 |  | 4 |  |  | 2.25
Week5 |  | 5 |  |  | 8
Week6 |  | 6 |  |  | 4.8
Week7 |  | 7 |  |  | 41
Week8 |  | 8 |  |  | 12
Week9 |  | 9 |  |  | 19.5
Week10 |  | 10 |  |  | 0
Total effort |  |  |  |  | 106.8

## Reports
The charts here update automatically

## Instructions
Using the activity tracker
At the end of each week, update the status of all activities completed during the week
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
After each release, look at the "reports" section to see charts of how much time has been spent so far, and what activities it has been spent on
Use the charts and data to identify needs for improvement